## GOODS
PROCUREMENT ENTITY: UNIVERSITY OF ENERGY AND NATURAL RESOURCES-SUNYANI PROCUREMENT PLAN-GOODS
PROJECT: REGIONAL CENTER FOR ENERGY AND ENVIRONMENTAL SUSTAINABILITY(RCEES)
BUDGET PERIOD: JAN - DEC 2020
SOURCE OF FUNDING: WORLD BANK GROUP, IGF & GOG |  |  |  | BASIC DATA |  |  | Tendering Period |  |  | Tender Evaluation |  | Contract Finalization |  | Goods Delivery
No. | Contract Package | Plan vs | Package No. | Estimated | Procurement | Approval/ | Preparation | Tender | Tender | Sub. Ten. | Approval by | Contract | Date Contract | Arrival of | Inspection
|  | Actual |  | Amount(GH¢) | Method | Authority | Ten. Doc | Invitation Date | Closing/Open. | Eva. Report. | Authority | Date | Signature | Goods | Final Accept.
Duration
1 | Printed Materials (Flyers, brochures) and Stationery | Plan | BA/UENR/RCEES/GD/001/20 | 150000 | RFQ | ETC | 09/03/20 | 16/03/20 | 23/03/20 | 30/03/20 | 06/04/20 | 15/04/20 | 22/04/20 | 07/05/20 | 07/05/20
Actual
2 | Teaching and Learning | Plan | BA/UENR/RCEES/GD/002/20 | 20000 | RFQ | HoE | 03/02/20 | 10/02/20 | 17/02/20 | 24/02/20 | 02/03/20 | 10/03/20 | 17/03/20 | 31/03/20 | 31/03/20
| Aids/Materials | Actual
3 | I.C.T Equipment and Accessories | Plan | BA/UENR/RCEES/GD/003/20 | 150000 | RFQ | ETC | 08/01/20 | 15/01/20 | 22/01/20 | 29/01/20 | 05/02/20 | 12/02/20 | 19/02/20 | 11/03/20 | 11/03/20
Actual
4 | Office Equipment and | Plan | BA/UENR/RCEES/GD/004/20 | 100000 | RFQ | HoE | 01/07/20 | 08/07/20 | 15/07/20 | 22/07/20 | 29/07/20 | 07/08/20 | 14/08/20 | 28/08/20 | 28/08/20
| Accessories | Actual
5 | Accounting Software | Plan | BA/UENR/RCEES/GD/005/20 | 100000 | RFQ | HoE | 09/03/20 | 16/03/20 | 23/03/20 | 30/03/20 | 06/04/20 | 14/04/20 | 21/04/20 | 20/05/20 | 20/05/20
Actual
6 | Desktop Computers & | Plan | BA/UENR/RCEES/GD/006/20 | 100,000.00 | RFQ | HoE | 08/01/20 | 15/01/20 | 22/01/20 | 29/01/20 | 05/02/20 | 12/02/20 | 19/02/20 | 11/03/20 | 11/03/20
| Laptops | Actual
7 | Supply of Office Furniture | Plan | BA/UENR/RCEES/GD/007/20 | 100000 | RFQ | HoE | 01/07/20 | 08/07/20 | 15/07/20 | 22/07/20 | 29/07/20 | 07/08/20 | 14/08/20 | 28/08/20 | 28/08/20
| (Tables,Workstation, Cabinet) | Actual
8 | Maintenance and | Plan | BA/UENR/RCEES/GD/008/20 | 100,000.00 | RFQ | HoE | 03/02/20 | 10/02/20 | 17/02/20 | 24/02/20 | 02/03/20 | 10/03/20 | 17/03/20 | 01/04/20 | 01/04/20
| Sundry Items | Actual
9 | Supply and Installation of | Plan | BA/UENR/RCEES/GD/009/20 | 5000000 | NCT | CTRC | 01/07/20 | 08/07/20 | 15/07/20 | 22/07/20 | 29/07/20 | 07/08/20 | 14/08/20 | 28/08/20 | 28/08/20
| Laboratory Equipment | Actual
10 | Vehicles(Bus and Station | Plan | BA/UENR/RCEES/GD/010/20 | 2000000 | NCT | CTRC | 08/01/20 | 15/01/20 | 29/01/20 | 12/02/20 | 26/02/20 | 04/03/20 | 11/03/20 | 08/04/20 | 08/04/20
| Wagon) | Actual
11 | Tonners and Catridges | Plan | BA/UENR/RCEES/GD/011/20 | 20000 | RFQ | HoE | 04/05/20 | 11/05/20 | 18/05/20 | 25/05/20 | 01/06/20 | 08/06/20 | 15/06/20 | 13/07/20 | 13/07/20
Actual
| Total Cost | Plan |  | 7640000
Actual
Page 1