## GOODS
PROCUREMENT ENTITY: UNIVERSITY OF ENERGY AND NATURAL RESOURCES-SUNYANI PROCUREMENT PLAN-GOODS
PROJECT: REGIONAL CENTER FOR ENERGY AND ENVIRONMENTAL SUSTAINABILITY(RCEES)
BUDGET PERIOD: JAN - DEC 2021
SOURCE OF FUNDING: WORLD BANK GROUP, IGF & GOG |  |  |  | BASIC DATA |  |  | Tendering Period |  |  | Tender Evaluation |  | Contract Finalization |  | Goods Delivery
No. | Contract Package | Plan vs | Package No. | Estimated | Procurement | Approval/ | Preparation | Tender | Tender | Sub. Ten. | Approval by | Contract | Date Contract | Arrival of | Inspection
|  | Actual |  | Amount(GH¢) | Method | Authority | Ten. Doc | Invitation Date | Closing/Open. | Eva. Report. | Authority | Date | Signature | Goods | Final Accept.
Duration
1 | Printed Materials (Flyers, brochures) and Stationery | Plan | BA/UENR/RCEES/GD/001/21 | 150000 | NCT | ETC | 11/01/21 | 18/01/21 | 08/02/21 | 15/02/21 | 22/02/21 | 01/03/21 | 08/03/21 | 22/03/21 | 22/03/21
Actual
2 | Teaching and Learning | Plan | BA/UENR/RCEES/GD/002/21 | 30000 | RFQ | HoE | 07/07/21 | 14/07/21 | 22/07/21 | 29/07/21 | 06/08/21 | 13/08/21 | 20/08/21 | 27/08/21 | 27/08/21
| Aids/Materials | Actual
3 | I.C.T Equipment and Accessories(Server etc.) | Plan | BA/UENR/RCEES/GD/003/21 | 172000 | NCT | ETC | 13/09/21 | 28/09/21 | 19/10/21 | 26/10/21 | 09/11/21 | 16/11/21 | 23/11/21 | 30/11/21 | 30/11/21
Actual
4 | Office Equipment and | Plan | BA/UENR/RCEES/GD/004/21 | 100000 | RFQ | HoE | 29/06/21 | 07/07/21 | 14/07/21 | 22/07/21 | 29/07/21 | 06/08/21 | 13/08/21 | 20/08/21 | 20/08/21
| Accessories | Actual
5 | Accounting Software | Plan | BA/UENR/RCEES/GD/005/21 | 100000 | RFQ | HoE | 24/06/21 | 02/07/21 | 09/07/21 | 16/07/21 | 26/07/21 | 02/08/21 | 10/08/21 | 17/08/21 | 17/08/21
Actual
6 | Desktop Computers & | Plan | BA/UENR/RCEES/GD/006/21 | 120,000.00 | NCT | ETC | 13/09/21 | 28/09/21 | 19/10/21 | 26/10/21 | 09/11/21 | 16/11/21 | 23/11/21 | 30/11/21 | 30/11/21
| Laptops | Actual
7 | Supply of Office Furniture | Plan | BA/UENR/RCEES/GD/007/21 | 100000 | RFQ | HoE | 03/02/21 | 10/02/21 | 17/02/21 | 24/02/21 | 03/03/21 | 10/02/21 | 17/03/21 | 24/03/21 | 24/03/21
| (Tables,Workstation, Cabinet) | Actual
8 | Maintenance and | Plan | BA/UENR/RCEES/GD/008/21 | 100,000.00 | RFQ | HoE | 25/03/21 | 09/04/21 | 16/04/21 | 23/04/21 | 30/04/21 | 07/05/21 | 17/05/21 | 24/05/21 | 24/05/21
| Sundry Items | Actual
9 | Supply and Installation of | Plan | BA/UENR/RCEES/GD/009/21 | 9849937 | NCT | CTRC | 05/07/21 | 12/07/21 | 03/08/21 | 11/08/21 | 18/08/21 | 25/08/21 | 01/09/21 | 23/09/21 | 30/09/21
| Laboratory Equipment | Actual
10 | Tonners and Catridges | Plan | BA/UENR/RCEES/GD/010/21 | 20000 | RFQ | HoE | 11/01/21 | 18/01/21 | 25/01/21 | 01/02/21 | 08/02/21 | 15/02/21 | 22/02/21 | 01/03/21 | 01/03/21
Actual
| Total Cost | Plan |  | 10521937
Actual
Page 1

## Consultancy Services
Procurement Entity |  | University of Energy and Natural Resources, Sunyani Procurement Plan-Consultancy Services
Budget Period |  | Jan-Dec, 2021
Source of Funding: WORLD BANK GROUP, GOG, IGF | [5 empty] | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  | Negotiations |  |  | Contract Finalization |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Prep & Submission by Executing Agency | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract ward | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report
| Duration | [5 empty] | 1 Wk | 2-4 Wks | 1 Wk | 1 Wk | 2 Wks | 2 Wks | 1 -2Wks | 1 Wk | 1 Wk | 1 Wk | 2 Wks | 2 Wks | 2-4 Wks | 2-4 Wks
Provision of Auditing Services | Plan | BA/UENR/RCEES/CS/001/21 | 50000 | QCBS | ETC | 22/02/21 | 01/03'/21 | 22/03/21 | 29/03/21 | 2021-07-04 | 21/04/21 | 2021-05-05 | 12/05/21 | 20/05/21 | 28/05/21 | 2021-04-05 | 18/05/21 | 02/06/21 | 02/08/21 | 01//09/21
Actual
Total Cost | Plan |  | 50000
Actual
Fill gray cells only!